## Example
20 Week Period
Goal # | Goal Description | Activity | Responsible Parties | Accountable Party | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Implement and analyze data use survey | Determine what you would like to discover from data use survey | Culture Building Lead(s), data team | Culture Building Lead(s) | bar: 20 Week Period 1 to 20 Week Period 2
|  | Develop and disseminate data use survey to staff | Culture Building Lead(s) | Culture Building Lead(s) | bar: 20 Week Period 1 to 20 Week Period 5
|  | Analyze survey results and discover potential growth areas | Culture Building Lead(s) | Culture Building Lead(s) | bar: 20 Week Period 5 to 20 Week Period 6
2 | Define culture building objectives & work plan | Identify champions of improved data use | Culture Building Lead(s), champions | Culture Building Lead(s) | 20 Week Period 2: 2; 20 Week Period 3: 2; 20 Week Period 4: 2
|  | Hold objectives and planning discussion with champions, defining roles | Culture Building Lead(s), Data Supporters across org depts/sectors, data team | Culture Building Lead(s) | 20 Week Period 5: 2; 20 Week Period 6: 2
3 | Implement data literacy workshop | Determine objectives and design data literacy workshop | Culture Building Lead(s), champions, data team | Culture Building Lead(s) | 20 Week Period 6: 3; 20 Week Period 7: 3; 20 Week Period 8: 3
|  | Promote data literacy workshop among staff | Champions | Culture Building Lead(s) | 20 Week Period 8: 3; 20 Week Period 9: 3; 20 Week Period 10: 3
|  | Facilitate and attend data literacy workshop | Org staff, champions, Culture Building Lead(s) | Culture Building Lead(s) | 20 Week Period 10: 3; 20 Week Period 11: 3
4 | Develop and implement data security policies | Use survey analysis, discussions with champions, and observations to discover data security policy priorities | Culture Building Lead(s), data team | Culture Building Lead(s) | 20 Week Period 6: 4; 20 Week Period 7: 4
|  | Review data hygiene checklists to discover "quick wins" for security policies | Culture Building Lead(s), data team | Culture Building Lead(s) | 20 Week Period 8: 4; 20 Week Period 9: 4
|  | Review the NIST Cybersecurity Framework, and relevant templates, to assist development of security policies | data team | Culture Building Lead(s) | 20 Week Period 9: 4; 20 Week Period 10: 4
|  | Develop security policies in priority and "quick win" areas | data team | Culture Building Lead(s) | 20 Week Period 11: 4; 20 Week Period 12: 4; 20 Week Period 13: 4
|  | Review/adjust policies with champions and follow through org process for policy implementation | Culture Building Lead(s), data team, champions | Culture Building Lead(s) | 20 Week Period 13: 4; 20 Week Period 14: 4; 20 Week Period 15: 4
|  | Hold staff listening session to both launch new policies and listen to feedback | Culture Building Lead(s), data team | Culture Building Lead(s) | 20 Week Period 16: 4; 20 Week Period 17: 4
Note on F2: Mark Goal # for each week planned for an activity -Prem Durairaj

## Template
20 Week Period
Goal # | Goal Description | Activity | Responsible Parties | Accountable Party | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1
Note on F2: Mark Goal # for each week planned for an activity -Prem Durairaj